## Blad1
Project 3 | User story # | Work item # | Day 1 | Day 2 | Day 3 | End
Sprint 1 | User story 0 | Work item 0.1 | 1 | 1 | 3
Sprint 1 | User story 0 | Work item 0.2 | 0 | 0 | 0
Sprint 1 | User story 1 | Work item 1.1 | 5 | 4 | 3
Sprint 1 | User story 1 | Work item 1.2 | 5 | 0 | 1
Sprint 1 | User story 1 | Work item 1.3 | 5 | 0 | 1
Sprint 1 | User story 2 | Work item 2.1 | 5 | 3 | 0
Sprint 1 | User story 2 | Work item 2.2 | 5 | 3 | 1
Ideal | 30 | 21 | 14 | 7 | 0
Actual | 30 | 17 | 7 | 7 | 0