## PRODUCT BACKLOG
PRODUCT BACKLOG (Robotron 2084)
ID | Feature | Category | Priority | Sprint 1 | Sprint 2 | Sprint 3
0 | Character is able to move | Character | M | To do
1 | Character is able to shoot horizontally and vertically | Character | M | To do
2 | The game keeps track of your score | Stage | M | To do
3 | Robots are able to chase the player | Robots | M |  | To do
4 | Collision with a robot causes the player to lose a life | Character | M |  | To do
5 | When you reach a certain amount of points, you go to the next stage | Stage | M |  | To do
6 | Collision with a human causes you to earn points | Character | M |  | To do
7 | If you shoot a robot the robot dies | Robots | M |  | To do
8 | Collision with a mine causes the player to lose a life | Character | M |  | To do
9 | Reaching a certain amount of points will earn you a life | Character | S |  |  | To do
10 | If a robot collides with a human, the human becomes a robot | Human | S |  |  | To do
11 | The game keeps track of your stage | Stage | S |  |  | To do
12 | The game has sound effects | Stage | C |  |  | To do
13 | Character is able to shoot diagonally | Character | C |  |  | To do
14 | Create a main menu in which you can start and exit the game | Stage | C |  |  | To do
15 | The program has to run on dekstop and android | Game | M |  |  | To do
16
17
18
19
20
21
22
23
24
25

## SPRINT 1 BACKLOG
SPRINT 1 BACKLOG
ID | User story | Priority | Time Estimation | Tasks | Acceptance criteria
0 | As a user I want to be able to move my character, so that I am able to play the game. | M | 5 | - Sprite rendering - Sprite interpolation based on user input | - The character must be able to move horizontally and vertically - There must be a joystick which consists of 4 buttons to move my character (up, down, left, right) - The character has to be distinguishable from the other sprites on the screen
1 | As a user I want my character to be able to shoot vertically and horizontally, so that I am able to shoot and kill robots. | M | 7 | - Implement projectiles - Be able to shoot on the X and Y axis - Projectiles are fried on interval going in the direction the player is facing/moving towards | - The projectile has to move straight in a horizontal or vertical line - The projectile has to be rendered on the screen
2 | As a user I want to be able to see my score, so that I can advance to the next stage | M | 3 | - Select a font for the score - Keep track of the player's score and draw it on the screen - When the score hits a certain number, change the screen | - The font has to be readable - Go to the next stage when you kill all the robots

## SPRINT 2 BACKLOG
SPRINT 2 BACKLOG
ID | User story | Priority | Time Estimation | Tasks | Acceptance criteria
| As a user I want the robots to be able to chase me as a player, so that the game is challenging and rewarding. | M | 15 | - Robots can walk -Robots are able to turn - Select a sprite for the robot | - Robots are able to detect where the character is located on the screen - There are different kind of robots - The robots can move on both the X and Y axis
| As a user I want to lose a life when a robot hits me, so that the game stays challenging | M | 5 | - Character has to have lives - Show lives on top like the original game - Detect collision with robots and the character - Select a sprite for the life symbol | - Character loses a life when a robot hits him - If life reaches zero, the character dies - The sprite has to reflect the original symbol
| As a user I want to receive points when I collide with a human, so that I am able to advance to the next stage | M | 5 | - Detect collision with humans and the character - Humans can walk - Humans are able to turn - Select a sprite for the humans | - Character receives points when they collide with a human - Humans can move on both the X and Y axis - The sprite has to reflect the original human from the game - Humans are placed randomly on the level
| As a user I want to be able to kill a robot when I shoot it, so that I can maneuver my way through the stage | M | 5 | - Detect collision between bullets and robots - Bullet speed is adequate - The robot dissapears from the screen when shot | - Destroy the robot when hit - The bullet travels fast enough so that the player does not catch up to it
| As a user I want to lose a life when I hit a mine, so that the game does not get to easy | M | 5 | - Detect collision between character and mine - Character loses a life when the mine is hit - Select the sprite for the mine | - Character loses a life when he touches a mine - The sprite has to reflect the original mine from the game - Mines are placed randomly on the level
| Introduce full Android support for the endproduct | M | 20 | - Deploy application to android device or emulator - Test features on android device or emulator - Fix potential issues on android device or emulator | - Application must be able to run on android device or emulator

## SPRINT 3 BACKLOG
SPRINT 3 BACKLOG
ID | User story | Priority | Time Estimation | Tasks | Acceptance criteria
As a user I want to receive a life when I reach a certain amount of points, so that I have small goals in the stages themselves to work towards
As a user I want humans to turn into robots when a robot touches them, so that there is a sense of urgency to safe them
As a user I want to be able to see the stage that I am in, so that I am aware of how far I have advanced in the game
As a user I want to have sound effects in the game, so that the game is engaging and I can identify events in the game with sounds
As a user I want my character to be able to shoot diagonally, so that I am amble to shoot robots in multiple ways
As a user I want to have a main menu, so that I can clearly see which game I am playing and wether I want to start the game or exit the game
As a user I want to be able to play the game on android and desktop, so that I can play comfortably from home but also on the road